## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
1 | Upload a list of ingredients | Sprint 1 | Edrico, Bryan, Bintang, Vincent | 2024-01-05 | 2024-07-05 | No | Yes | High | Not Started | 8 | No
| Create Personal Database | Sprint 1 | Edrico | 2024-01-05 | 2024-02-05 | Yes | Yes | High | Not Started | 2 | Yes | This section is for the drop-down list
| Create Interface for Uploading Ingredients | Sprint 1 | Bintang, Vincent | 2024-02-05 | 2024-04-05 | Yes | Yes | Medium | Not Started | 4 | Yes | Yes | High | Complete
| Setup API to Personal Database | Sprint 1 | Bryan | 2024-05-05 | 2024-07-05 | Yes | Yes | High | Not Started | 2 | Yes | No | Medium | In Progress
2 | view several food recipes based on uploaded ingredients | Sprint 2 | Edrico, Bryan, Bintang, Vincent | 2024-08-05 | 14/5/2024 | No | No | High | Not Started | 12 | No |  | Low | Not Started
| Create Interface for Generating Recipe | Sprint 2 | Bintang | 2024-08-05 | 2024-09-05 | Yes | No | High | Not Started | 3 | Yes
| Setup API to Personal Database | Sprint 2 | Edrico | 2024-09-05 | 2024-09-05 | Yes | No | High | Not Started | 1 | Yes
| Code for Automatically Generating Prompt | Sprint 2 | Bryan | 2024-10-05 | 2024-10-05 | Yes | No | Medium | Not Started | 1 | Yes
| Setup API to GPT | Sprint 2 | Edrico | 2024-11-05 | 2024-11-05 | Yes | No | Medium | Not Started | 2 | Yes
| Create Interface for Output (Recipe) | Sprint 2 | Vincent | 2024-11-05 | 2024-12-05 | Yes | No | High | Not Started | 2 | Yes
| Code to Keep Track of Selected Recipes | Sprint 2 | Bintang | 2024-12-05 | 14/5/2024 | Yes | No | Medium | Not Started | 1 | Yes
| Setup API to Public Database (common recipe, etc) | Sprint 2 | Bryan | 14/5/2024 | 14/5/2024 | Yes | No | High | Not Started | 2 | Yes
3 | view commonly selected recipe | Sprint 3 | Edrico, Bryan, Bintang, Vincent | 15/5/2024 | 22/5/2024 | No | No | Medium | Not Started | 9 | No
| Create Interface for viewing common selected recipe | Sprint 3 | Bintang | 15/5/2024 | 16/5/2024 | Yes | No | High | Not Started | 3 | Yes
| Setup API to Public Database (common recipe, etc) | Sprint 3 | Edrico | 17/5/2024 | 18/5/2024 | Yes | No | High | Not Started | 1 | Yes
| Create Code to Import X most selected Recipe | Sprint 3 | Bryan | 19/5/2024 | 20/5/2024 | Yes | No | Medium | Not Started | 2 | Yes
| Create Interface for displaying selected Recipe | Sprint 3 | Vincent | 20/5/2024 | 22/5/2024 | Yes | No | High | Not Started | 3 | Yes
4 | generate recipes that match my taste preferences based on available or additional ingredients | Sprint 4 | Edrico, Bryan, Bintang, Vincent | 23/5/2024 | 30/5/2024 | No | No | Medium | Not Started | 11 | No
| Setup API to Personal Database | Sprint 4 | Edrico | 23/5/2024 | 23/5/2024 | Yes | No | High | Not Started | 1 | Yes
| Create Interface Ingredient Choice (Available/Additional) | Sprint 4 | Bintang | 24/5/2024 | 26/5/2024 | Yes | No | High | Not Started | 3 | Yes
| Code to Read Tagging of Commonly Used Ingredients and Generate Prompt | Sprint 4 | Bryan | 27/5/2024 | 27/5/2024 | Yes | No | Medium | Not Started | 2 | Yes
| Setup API to GPT | Sprint 4 | Bintang | 28/5/2024 | 28/5/2024 | Yes | No | High | Not Started | 2 | Yes
| Create Interface for Output (Recipe) | Sprint 4 | Vincent | 29/5/2024 | 30/5/2024 | Yes | No | High | Not Started | 3 | Yes
Sprint 6
Sprint 7
CLICK HERE TO CREATE IN SMARTSHEET