## Agile Sprint Backlog-DishCraft
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8 | Edrico, Bryan, Bintang, Vincent | Not Started
Create Personal Database | 2 | Edrico | Not Started | 2 | 2 | 1 | 1 | 0 | 0 | 0
Create Interface for Uploading Ingredients | 4 | Bintang, Vincent | Not Started | 4 | 4 | 4 | 2 | 2 | 1 | 0
Setup API to Personal Database | 2 | Bryan | Not Started | 2 | 1 | 1 | 0 | 0 | 0 | 0
User Story #2 | 12 | Edrico, Bryan, Bintang, Vincent | Not Started
Create Interface for Generating Recipe | 3 | Bintang | Not Started | 3 | 3 | 2 | 2 | 2 | 0 | 0
Setup API to Personal Database | 1 | Edrico | Not Started | 1 | 1 | 0 | 0 | 0 | 0 | 0
Code for Automatically Generating Prompt | 1 | Bryan | Not Started | 1 | 1 | 0 | 0 | 0 | 0 | 0
Setup API to GPT | 2 | Edrico | Not Started | 2 | 1 | 1 | 1 | 0 | 0 | 0
Create Interface for Output (Recipe) | 2 | Vincent | Not Started | 2 | 2 | 1 | 1 | 0 | 0 | 0
Code to Keep Track of Selected Recipes | 1 | Bintang | Not Started | 1 | 1 | 1 | 0 | 0 | 0 | 0
Setup API to Public Database (common recipe, etc) | 2 | Bryan | Not Started | 2 | 2 | 2 | 1 | 0 | 0 | 0
User Story #3 | 9 | Edrico, Bryan, Bintang, Vincent | Not Started
Create Interface for viewing common selected recipe | 3 | Bintang | Not Started | 3 | 3 | 2 | 2 | 0 | 0 | 0
Setup API to Public Database (common recipe, etc) | 1 | Edrico | Not Started | 1 | 1 | 0 | 0 | 0 | 0 | 0
Create Code to Import X most selected Recipe | 2 | Bryan | Not Started | 2 | 1 | 1 | 0 | 0 | 0 | 0
Create Interface for displaying selected Recipe | 3 | Vincent | Not Started | 3 | 3 | 3 | 1 | 0 | 0 | 0
User Story #4 | 11 | Edrico, Bryan, Bintang, Vincent | Not Started
Setup API to Personal Database | 1 | Edrico | Not Started | 1 | 1 | 0 | 0 | 0 | 0 | 0
Create Interface Ingredient Choice (Available/Additional) | 3 | Bintang | Not Started | 3 | 3 | 1 | 1 | 1 | 1 | 0
Code to Read Tagging of Commonly Used Ingredients and Generate Prompt | 2 | Bryan | Not Started | 2 | 2 | 0 | 0 | 0 | 0 | 0
Setup API to GPT | 2 | Bintang | Not Started | 2 | 1 | 1 | 1 | 1 | 0 | 0
Create Interface for Output (Recipe) | 3 | Vincent | Not Started | 3 | 3 | 1 | 0 | 0 | 0 | 0
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 40 | 36 | 22 | 13 | 6 | 2 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.