## BLANK - Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | DishCraft |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Edrico |  |  | 2024-05-01 | 2024-05-28 | 0% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Bryan | 8 | 2024-05-01 | 2024-05-06 | 6 | Not Started
No | Create Personal Database |  | Edrico | 2 | 2024-05-01 | 2024-05-06 | 6 | Not Started
No | Create Interface for Uploading Ingredients |  | Bintang,Vincent | 4 | 2024-05-01 | 2024-05-06 | 6 | Not Started
No | Setup Api to Personall Database |  | Bryan | 2 | 2024-05-01 | 2024-05-06 | 6 | Not Started
No | SPRINT 2 |  | Edrico | 13 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Create Interface for Generating Recipe |  | Bintang | 3 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Setup API to Personal Database |  | Edrico | 2 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Code for Automatically Generating Prompt |  | Bryan | 1 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Setup API to GPT |  | Edrico | 2 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Create Interface for Output (Recipe) |  | Vincent | 2 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Code to Track Selected Recipes |  | Bintang | 1 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | Setup API to Public Database (common recipe, etc) |  | Bryan | 2 | 2024-05-08 | 2024-05-13 | 6 | Not Started
No | SPRINT 3 |  | Edrico | 8 | 2024-05-15 | 2024-05-20 | 8 | Not Started
No | Create Interface for viewing common selected recipe |  | Bintang | 2 | 2024-05-15 | 2024-05-20 | 8 | Not Started
No | Setup API to Public Database (common recipe, etc) |  | Edrico | 1 | 2024-05-15 | 2024-05-20 | 8 | Not Started
No | Create Code to Import X most selected Recipe |  | Bryan | 2 | 2024-05-15 | 2024-05-20 | 8 | Not Started
No | Create Interface for displaying selected Recipe |  | Vincent | 3 | 2024-05-15 | 2024-05-20 | 8 | Not Started
No | SPRINT 4 |  | Bryan | 11 | 2024-05-23 | 2024-05-28 | 6 | Not Started
No | Setup API to Personal Database |  | Edrico | 1 | 2024-05-23 | 2024-05-28 | 6 | Not Started
No | Create Interface Ingredient Choice (Available/Additional) |  | Bintang | 3 | 2024-05-23 | 2024-05-28 | 6 | Not Started
No | Code to Read Tagging of Commonly Used Ingredients and Generate Prompt |  | Bryan | 2 | 2024-05-23 | 2024-05-28 | 6 | Not Started
No | Setup API to GPT |  | Bintang | 2 | 2024-05-23 | 2024-05-28 | 6 | Not Started
No | Create Interface for Output (Recipe) |  | Vincent | 3 | 2024-05-23 | 2024-05-28 | 6 | Not Started
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.